## How_To
RENOVIT Technology CAPEX Model
Current baseline: 10kt/year line for limestone-based finishing materials
Hybrid recommended: core equipment new/verified, auxiliary used/local if inspected.

## Equipment_CAPEX
equipment_item | phase | criticality | capacity | used_low_eur | used_high_eur | hybrid_low_eur | hybrid_high_eur | new_low_eur | new_high_eur | source_hint | status | notes
Micronization mill | Phase 1 - Micronization and sorting | critical | 5 t/h under 100 micron | 60000 | 90000 | 100000 | 140000 | 180000 | 250000 | China / Alibaba for new; Machineryline for used | rfq_baseline | Core quality bottleneck for glet extra-white and calcium carbonate filler
Vibrating sieve / classifier | Phase 1 - Micronization and sorting | critical | 5 t/h 0.1-2 mm | 15000 | 25000 | 30000 | 40000 | 50000 | 70000 | OLX RO / used EU / Turkey | rfq_baseline | Needed for decorative mineral render fractions and repeatability
Screw conveyor | Phase 1 - Micronization and sorting | important | 10 t/h | 8000 | 12000 | 15000 | 20000 | 25000 | 35000 | Local MD / RO fabrication | rfq_baseline | Check dust sealing and compatibility with fine calcium carbonate
Industrial dry mixer | Phase 2 - Mixing and dosing | critical | 2 t batch / around 10 t/h | 25000 | 40000 | 50000 | 70000 | 90000 | 130000 | Poland / Turkey / China | rfq_baseline | Hybrid recommended; homogeneity is product-quality critical
Additive dosing units | Phase 2 - Mixing and dosing | critical | 4 components | 10000 | 15000 | 20000 | 30000 | 40000 | 60000 | Poland / Turkey / China | rfq_baseline | Precision around +/-0.5 percent is critical for polymer / cellulose additives
Dosing scale | Phase 2 - Mixing and dosing | critical | 2 t | 5000 | 8000 | 10000 | 15000 | 20000 | 25000 | Regional industrial suppliers | rfq_baseline | Must integrate with mixer and recipe control
Adjustable bag filling line | Phase 3 - Hybrid 20/25kg packing | critical | 600 bags/h 15-30 kg | 40000 | 60000 | 80000 | 120000 | 150000 | 220000 | China / Turkey / dry mortar suppliers | rfq_baseline | Essential: must handle both 20kg and 25kg bags with dosing accuracy
Bag stitcher / sealer | Phase 3 - Hybrid 20/25kg packing | important | 600 bags/h | 5000 | 8000 | 12000 | 18000 | 25000 | 35000 | Regional suppliers | rfq_baseline | Check bag type: open mouth vs valve bags
Labeler / printer | Phase 3 - Hybrid 20/25kg packing | important | 600 bags/h | 3000 | 5000 | 8000 | 12000 | 15000 | 25000 | Regional suppliers | rfq_baseline | Traceability and compliance labels
Semi-automatic palletizer | Phase 3 - Hybrid 20/25kg packing | important | 1 pallet / 5 min | 15000 | 25000 | 35000 | 50000 | 70000 | 100000 | Used EU / Turkey / China | rfq_baseline | Semi-auto used is acceptable at start if warehouse flow is simple
Raw limestone silo | Auxiliary infrastructure | important | 200 t | 20000 | 30000 | 20000 | 30000 | 20000 | 30000 | Local fabrication / second-hand silos | rfq_baseline | Moisture protection and dust control required
Finished product silo | Auxiliary infrastructure | important | 100 t | 15000 | 25000 | 15000 | 25000 | 15000 | 25000 | Local fabrication / second-hand silos | rfq_baseline | Protect finished dry mix from humidity
Electrical connection | Auxiliary infrastructure | critical | 315 kW three-phase | 10000 | 15000 | 10000 | 15000 | 10000 | 15000 | Local MD | rfq_baseline | Needs power audit; update if 10kt line requires more connected load
Water connection | Auxiliary infrastructure | important | 10 m3/day | 5000 | 8000 | 5000 | 8000 | 5000 | 8000 | Local MD | rfq_baseline | Mainly facility / lab use; dry process should not consume much water
Quality laboratory | Auxiliary infrastructure | critical | EN 998-1 / product tests baseline | 25000 | 35000 | 25000 | 35000 | 25000 | 35000 | Local lab equipment / outsource hybrid | rfq_baseline | Can outsource some tests but in-house baseline is recommended
Office and changing room | Auxiliary infrastructure | important | 6 employees | 10000 | 15000 | 10000 | 15000 | 10000 | 15000 | Local MD | rfq_baseline | Include only if existing facilities cannot be reused

## Capacity_Scenarios
scenario | finished_capacity_t_year | finished_capacity_t_month | capex_low_eur | capex_high_eur | breakeven_t_year | breakeven_t_month | roi_3y_range | verdict | status | notes
Pilot | 3000 | 250 | 160000 | 300000 | 1000 | 83 | To validate | Risk | working_assumption | Useful only for recipe / buyer validation; may underuse fixed costs
Small industrial | 5000 | 417 | 220000 | 450000 | 1400 | 117 | To validate | Conditional | working_assumption | Can work if capital is constrained but 10kt equipment may be preferable
Recommended 10kt hybrid | 10000 | 833 | 445000 | 643000 | 1800 | 150 | To validate | OPTIMAL RFQ BASELINE | working_assumption | Core plus auxiliary before repair reserve / contingency; replace with supplier offers
Industrial 20kt | 20000 | 1667 | 900000 | 1500000 | 3500 | 292 | To validate | Industrial | working_assumption | Use after demand and financing are validated; new equipment becomes more logical

## Implementation_Phases
phase | decision_name | timeframe | capacity_target | capex_logic | equipment_strategy | key_gate | notes
Phase 0 | Technical and commercial due diligence | 0-2 months | No production | Minimal spend | None | Lab quality + market price + partner terms | Do not buy equipment before quality and offtake validation
Phase 1 | Recommended 10kt/year hybrid launch line | 3-6 months | 10000 t/year | around 445-643k EUR before repair reserve / contingency | Hybrid core + used auxiliary | Validated quality + 3 buyer conversations + 3 supplier RFQs + acceptable payback | Target 20kg and 25kg bags with 600 bags/hour packing line; do not treat profit as confirmed until prices are validated
Phase 1 optional | Capital-constrained 5kt/year starter | 3-6 months | 5000 t/year | scaled-down CAPEX if 10kt is not acceptable | Used / hybrid line | Same quality and buyer gates as Phase 1 | Use only if capital appetite is too low for the recommended 10kt baseline
Phase 2 | Add capacity to 20kt/year | 6-18 months | 20000 t/year | Incremental CAPEX | Hybrid plus selective new bottleneck equipment | Demand above phase 1 capacity + stable operations | Add micronization / sorting / packing / silo modules
Phase 3 | New industrial line | 18+ months | 20000+ t/year | 900k-1.5M+ EUR | New equipment for core process | Proven margins + distribution + financing capacity | Use new line when uptime and scale matter more than cheap CAPEX

## Used_vs_New
criterion | used_equipment | hybrid_equipment | new_equipment | phase_1_weight | decision_note
CAPEX core 10kt | 186-288k EUR before auxiliary | 360-515k EUR before auxiliary | 665-950k EUR before auxiliary | high | Auxiliary infrastructure of 85-128k EUR must be added unless already available on site
Delivery speed | 4-8 weeks working assumption | 6-12 weeks working assumption | 10-16 weeks working assumption | medium | Hybrid still supports launch speed while protecting core process risk
Reliability | Highest repair and downtime risk | Core items protected by new / refurbished choices | Warranty and lower early downtime | high | Use hybrid as baseline if CAPEX appetite allows
Quality risk | Risky for micronization and dosing unless inspected | Better control on mill mixer dosing and bagging | Best control and documentation | high | Quality matters more than purchase price for extra-white finishing products
Spare parts | Potentially local/regional | Mixed: local auxiliary plus imported core | May depend on imported supplier | medium | Check spare parts and service before signing
ROI speed | Faster if equipment works | Potentially best balance of CAPEX and uptime | Slower unless volume and price are validated | high | Do not call ROI confirmed before RFQ and buyer validation
Scalability | May become bottleneck around 10kt | Practical 10kt launch bridge | Best for 20kt+ industrial route | high | New equipment makes more sense after demand validation
Technical risk | Higher commissioning risk | Moderate commissioning risk | Lower commissioning risk | high | Need mechanical/electrical audit and acceptance test
Financing risk | Lower capital at risk | Balanced capital at risk | Higher capital at risk | high | Avoid overcapitalizing before product-market fit

## Process_Flow
stage_id | stage_name | equipment_key | capacity_10kt_year | input | output | owner_question | status | notes
1 | Limestone selection | Existing Volodeni operation | TBD | White limestone / limestone flour | Selected feedstock | Which Volodeni zones provide the whitest and most consistent material? | critical | Take coded samples by zone
2 | Internal transport | Trucks / loader / rail access | TBD | Selected limestone | Limestone at processing point | What is true EUR/t internal logistics cost? | open | Include Bratuseni rail option if relevant
3 | Pre-crushing / feed preparation | Crusher or existing preparation line | TBD | Limestone rock / coarse material | Prepared feed for milling | Is existing flour sufficient or do we need pre-crushing? | working_assumption | Depends on current product state
4 | Micronization | Micronizer / fine mill | TBD | Prepared limestone | Extra-fine calcium carbonate filler | What fineness is required for glet extra-white? | critical | Replaces gypsum calcination as main quality bottleneck
5 | Granulometric sorting | Sieves / classifier | TBD | Ground limestone | Controlled fractions | What fractions are needed for decorative render? | critical | Controls texture and repeatability
6 | Additive dosing | Dosing units | 2-8 percent of mix | Limestone filler + additives | Dosed blend | Which additives are needed for each recipe? | critical | Polymers cellulose lime/cement may drive cost
7 | Dry mixing | Industrial dry mixer | around 10 t/hour | Dosed blend | Homogeneous dry mix | Can mixer keep recipe consistency? | critical | Homogeneity affects claims and returns
8 | Quality control | Lab equipment | TBD | Lot samples | Approved / rejected lot | Which tests are done per batch? | critical | Whiteness granulometry adhesion setting time
9 | Bulk / product storage | Silo / big bags | TBD | Approved dry mix | Stored product | How much buffer stock is needed? | working_assumption | Moisture control is key
10 | Bag filling | Adjustable 20/25kg bagging machine | 600 bags/hour | Bulk product | Filled bags | Can line handle both 20kg and 25kg formats? | critical | Commercial bottleneck for retail-ready product
11 | Stitching and printing | Bag stitcher + printer | TBD | Filled bags | Sealed labelled bags | What label / compliance information is required? | open | Connects quality and product readiness
12 | Palletizing | Manual or forklift-assisted palletizing | TBD | Sealed bags | Palletized finished goods | Manual now or robot later? | working_assumption | Robot likely not needed in phase 1
13 | Finished goods storage and loading | Forklift + warehouse | TBD | Pallets | Ready-to-ship product | How many days of finished goods stock are needed? | open | Needs dry warehouse and moisture control

## Additives_Lab
item | type | working_range_or_need | role | price_working_range_eur_t | status | notes
Cellulose ether / water-retention additive | additive | TBD by recipe | Workability and water retention | 2000-6000 | working_assumption | Essential for glet / mortar recipes; validate dosage with technologist
Polymer / redispersible powder | additive | TBD by recipe | Adhesion flexibility and performance | 2500-7000 | working_assumption | Can dominate additive cost; avoid assumptions before formulation tests
Whitening / brightening additive | additive | TBD | Improves whiteness / visual sellability | 3000-5000 | working_assumption | Only if limestone whiteness is not sufficient for extra-white positioning
Anti-moisture / hydrophobic agent | additive | TBD | Improves storage stability | 1000-3000 | working_assumption | Check need based on packaging and warehouse humidity
Analytical balance | lab | required | Lab baseline |  | open | Define spec with lab / technologist
Moisture analyzer | lab | required | Raw material and finished dry mix moisture control |  | open | Important for storage stability and batching
Whiteness meter / colorimeter | lab | required or outsourced | Controls extra-white positioning and lot consistency |  | open | Can outsource initially but should be part of quality roadmap
Sieve set / particle size tools | lab | required | Fineness and fraction control |  | open | Needed for micronization / decorative texture control
Flow / workability tools | lab | required | Application behavior testing |  | open | Select exact tooling after product standard mapping
Adhesion / strength testing | lab | required or outsourced | Product performance validation for EN 998-1 / EN 12004 route |  | open | Can outsource accredited tests initially
Sample retention system | lab | required | Traceability and claims handling |  | open | Keep coded samples by batch and raw material zone